## Sheet1
| PRI 0-2 = immediate | PRI 3 = before M2020 team release (Feb) | PRI 4 = before MSL team release (April) |  | PRI 5 = eventually
Category | Priority | Improvement | Date Added | Date Pushed to Production | Date Finished in Development | Notes | Challenge
Administrative | 0 | -Ability to upload multiple sheets at once and move sample class and type to fields in uploaded file | 2016-11-17 | 2016-12-20 | 2016-12-20
Other | 0 | Put code on github, deal with license | 2016-11-17 | 2016-12-20 | 2016-12-20
Other | 0 | remove WWU link at top | 2016-11-17 | 2016-12-20 | 2016-12-20
Other | 0 | Greatly extend the maximum number of characters allowed for the database/sample description tag in uploaded data | 2016-12-16 | 2017-01-18 | 2017-01-15
Searching | 0 | Add field to metadata for "Sample Type" (options: mineral, mixture, whole rock, coating, volatile, other) Also, assign "mineral" for all spectra already in database | 2016-12-21 | 2017-01-18 | 2017-01-15
Uploading | 0 | Move Class, mineral type, sample type into upload form | 2017-01-18 | 2017-01-18 | 2017-01-18
Administrative | 1 | Remove "date accessed" from metadata | 2016-11-17 | 2016-12-20 | 2016-12-20
Administrative | 1 | -Now that “date uploaded” is a field being generated, it would be nice to be able to see that in the admin’s list of samples. | 2016-11-17 | 2017-01-18 | 2017-01-15
Administrative | 1 | Automatically capitalize mineral name | 2016-11-17 | 2016-12-20 | 2016-12-20
Graphing | 1 | replace activate/deactivate link with check box | 2016-11-17 | 2017-01-30 | 2017-01-09
Other | 1 | Make landing page look nice | 2016-11-17 | 2016-12-20 | 2016-12-20
Searching | 1 | -Ability to search for multiple minerals, classes, ID’s at once (e.g. if I want results for garnet AND gypsum). | 2016-11-17 | 2016-12-20 | 2016-12-20
Searching | 1 | -Add in ability to search by min/max spectral range as some people might only be interested in things observed in specific regions of the electromagnetic spectrum. Search for ANY data in a range, or ONLY data in this range | 2016-11-17 | 2017-01-23 | 2017-01-22
Results | 1 | -Display exact number of results meeting search criteria on the results page and also the number of different minerals (by mineral name) meeting search criteria. Restrict display to 50 on a page and display "showing results 1-50 of xxxx results" with links at bottom to next results page | 2016-11-17 | 2017-01-30 | 2017-01-26
Other | 1 | Add links to other databases | 2016-12-01 | 2017-02-07 | 2017-02-07
Searching | 1 | Fix "Database of Origin" dropdown options (remove one of the duplicate "USGS" and the blank option) | 2017-01-27 | 2017-01-29 | 2017-01-29
Graphing | 2 | -Smooth out axes adjusting so that it is not so easy to drag the plot way off the page due to sudden jumps in axes values | 2016-11-17 | 2017-01-30 | 2017-01-29
Graphing | 2 | -Adding onto that, maybe find a way to prevent the user from dragging axes so far that there is no longer any portion of the spectra on the plot. | 2016-11-17 | 02/30/2017 | 2017-02-03 | This doesn't seem to be possible without a severe hit to performance. Every zoom event would be extremely slowed. I did add some limits help reduce the need for this feature.
Graphing | 2 | -More information in the list of minerals plotted at the bottom of the page (maybe set things to where if there are multiple minerals with the same name, the program will search through metadata to find fields that differ between each sample such as grain size or viewing geometry and display those values should they be different). Instead of just displaying ID, display mineral name too | 2016-11-17 | 2017-01-30 | 2017-01-29
Graphing | 2 | Prevent the data from "flattening out" when the axes are changed to make the data out of range (preferable to just not display data) | 2016-11-17 | 2017-01-30 | 2017-01-29
Graphing | 2 | add manual mix/max ranges for axes | 2016-11-17 | 2017-02-03 | 2017-02-03
Graphing | 2 | move axis labels ("Reflectance" and "Wavelength (nm)" to outside the graph | 2017-02-03 | 2017-02-05 | 2017-02-04
Uploading | 2 | Create a prompt when uploading spetra with duplicate IDs to ask the uploader whether or not they want to overwrite old data instead of automatically overwriting | 2016-12-16 | 2017-01-18 | 2017-01-18
searching | 2 | simplify search options on landing page (remove field for sample ID, remove "add search" option), and instead add an "advanced search" button, that will lead to a new search page with these options available | 2017-01-25 | 2017-02-05 | 2017-02-04
searching | 2 | remove the "exclusive data" vs "any data" switch, and instead add a option (a simple check box? or a button?) to turn on the min/max range search, with a label along the lines of: "search for spectra that include a given wavelength range" | 2017-02-03 | 2017-02-05 | 2017-02-04
Searching | 2 | Add drop-down selection for "sample type" on search home page | 2017-01-27 | 2017-02-05 | 2017-02-04
Searching | 2 | Add "Mineral Type" and "Sample Type" as columns in search results page | 2017-01-27 | 2017-02-05 | 2017-02-04
Administrative | 3 | -More specific error messages (‘server error’ is a pretty generic error message that is common but doesn’t help identify formatting problems). | 2016-11-17 |  |  | In order to fix server errors, I need to see what samples are being uploaded, or what specific actions caused the error.
Graphing | 3 | -Ability to turn tick marks for data points on (default off) in case anyone wants to zoom in and see these. | 2016-11-17 | 2017-02-12 | 2017-02-12
Graphing | 3 | Add an option to drop a vertical line | 2016-11-17 | 2017-02-12 | 2017-02-12
Other | 3 | -Maybe some page listing the people involved in this database project and their roles? Just so users of the database from other institutions are familiar with who we are. | 2016-11-17 | 2017-02-07 | 2017-02-07
Exporting | 3 | -Exporting search results should give a zip file with a more useful name as opposed to merely ‘spectra.’ Add ability for user to name file | 2016-11-17 | 2017-02-07 | 2017-02-07 | Because of "modern" internet standards, there isn't really an ideal way to go about doing this unless one is serving static files that aren't constantly edited. Because these CSV files are generated at runtime, the user can't simply link the browser to the file. I can redirect the user to another form which would basically let you choose the name with another download button that actually downloads the file with your input name. Or you can go into your browser's download settings and override this behavior so that it downloads ask you first rather than just saving to the download folder.
Results | 3 | sort search results alphanumerically by field | 2016-11-17 | 2017-02-21 | 2017-02-16 | Updated speed for multiple sorts
Other | 3 | Set up Goolge Analytics to track site activity | 2017-02-16 | 2017-02-21 | 2017-02-21
Other | 4 | -A link to download a PDF of (or a page displaying the information) the rules and guidelines for formatting spectral data to be added to the website so that people wishing to contribute can send us properly formatted data to look over and approve. | 2016-11-17 |  |  | Darian needs to finish editing the PDF | 3
Administrative | 4 | Add more options to drop down in admin page for "mark selected samples as" with all existing sample types (currently Mineral is only option) | 2017-02-22 |  |  |  | 2
Searching | 4 | On graph page, allow 'back' button to function as expected (return to search results), and allow users to share plots with others via unique URL. (Switch to GET form requests instead of POST form requests) | 2017-04-05 | 2017-04-08 | 2017-04-08 |  | Done
Searching | 4 | Fix buttons and header row at top of page while scrolling (so they're always visible at the top) | 2017-04-05 | 2017-04-08 | 2017-04-08 |  | Done
Searching | 4 | fix capitalization for "Only show Spectra With Data In Range" to "Only show spectra with data in range". Also, change "Min X (nm)" to "minimum wavelength (nm)" - and same for "Max X" | 2017-04-05 |  |  |  | 1
Graphing | 4 | Make it easier to see which spectra correspond to each color on the graph. Move the color box (that's currently at the far right of the metadata for each spectrum) so that it's next to the check box (to the left of ID) | 2017-04-05 |  |  | Moving the color box should be easy. Making further changes involving larger changes to the layout (eg. a two column layout with a key to the right of the graph or similar changes) will be more difficult but ultimately more useful | 1
Other | 4 | -A contact us page/field that sends messages out directly to people involved with maintaining the database; including the ability to report bugs, errors, suggestions, etc. | 2016-11-17 |  |  | This shouldn't be too difficult once we figure out how to get the local web service that is hosting the site to communicate with the email that Jim has given us. | 5
Other | 4 | Remove "sub-class" field from metadata | 2017-01-27 |  |  |  | 1
graphing | 4 | add check box next each item in legend with "report bad data" that will flag spectrum in database as something Darian should look at | 2017-02-27 |  |  |  | 3
Other | 4 | Add content to "About" page; find a more Mars-y background graphic for homepage; come up with a better title for the site (sexy acroynym?) | 2017-04-05 |  |  | Melissa needs to take care of all of this | 2
administrative | 4 | create email address for website help (something like help@spectro.geol.wwu.edu) that Darian and Melissa can access | 2017-02-27 |  |  |  | 3
Graphing | 5 | Add a "zoom to fit" or "restore" button | 2016-11-17 |  |  |  | 2
Graphing | 5 | -Adding of a band depth calculator (be able to select two points on the graph either by clicking or manually entering wavelength values and have the database do the simple band depth calculation for data between them). | 2016-11-17 |  |  |  | 4
Graphing | 5 | -Adding of a ratio calculator (be able to select two points on the graph either by clicking or manually entering wavelength values and have the database do a ratio of those two points). | 2016-11-17 |  |  |  | 4
Graphing | 5 | -Adding of a slope calculator (be able to select two points on the graph either by clicking or manually entering wavelength values and have the database measure the slope of the curve between those two points). | 2016-11-17 |  |  |  | 4
Graphing | 5 | Add an option to offset spectra | 2016-11-17 |  |  |  | 3
Graphing | 5 | Add option to display rover-simulated spectra | 2016-11-17 |  |  |  | 4
Graphing | 5 | Add option to normalize spectra to a given value | 2016-12-21 |  |  |  | 3
Other | 5 | Add option to upload a photo associated with a spectrum in the metadata | 2017-01-19
Graphing | 5 | Add option to fix the vertical line in place and add multiple lines | 2017-02-22